## Master Dependency
consumer | producer | dependency_type | domain | authority_owner | condition_or_reason | critical_path
M02 | M01 | HARD | Identity | M01 | All authenticated profile actors | Yes
M03 | M01 | HARD | Identity | M01 | Listing actor/owner | Yes
M04 | M01 | HARD | Identity | M01 | Learning/session actor | Yes
M05 | M01 | HARD | Identity | M01 | Event registration actor | Yes
M06 | M01 | HARD | Identity | M01 | Developer/claim actor | Yes
M07 | M01 | HARD | Identity | M01 | DBR subject | Yes
M08 | M01 | HARD | Identity | M01 | Dashboard subject | Yes
M09 | M01 | HARD | Identity | M01 | Admin actor | Yes
M10 | M01 | HARD | Identity | M01 | Authorization subject | Yes
M12 | M01 | HARD | Identity | M01 | Organization member | Yes
M13 | M01 | HARD | Identity | M01 | BYOK owner | Yes
M14 | M01 | HARD | Identity | M01 | Commercial actor/order ownership | Yes
M15 | M01 | HARD | Identity | M01 | Award recipient | Yes
M02 | M10 | HARD — AUTHORIZATION | Authorization | M10 | Profile/review access | Yes
M03 | M10 | HARD — AUTHORIZATION | Authorization | M10 | Listing scope/mutation access | Yes
M04 | M10 | HARD — AUTHORIZATION | Authorization | M10 | Learning/session access | Yes
M05 | M10 | HARD — AUTHORIZATION | Authorization | M10 | Event permission | Yes
M06 | M10 | HARD — AUTHORIZATION | Authorization | M10 | Developer/project/claim access | Yes
M07 | M10 | HARD — AUTHORIZATION | Authorization | M10 | DBR access/configuration | Yes
M08 | M10 | HARD — AUTHORIZATION | Authorization | M10 | Protected dashboard access | Yes
M09 | M10 | HARD — AUTHORIZATION | Authorization | M10 | Admin boundary | Yes
M12 | M10 | HARD — AUTHORIZATION | Authorization | M10 | Organization scope | Yes
M13 | M10 | HARD — AUTHORIZATION | Authorization | M10 | BYOK security | Yes
M14 | M10 | HARD — AUTHORIZATION | Authorization | M10 | Commercial operations | Yes
M15 | M10 | HARD — AUTHORIZATION | Authorization | M10 | Award access/admin | Yes
M02 | M09 | CONDITIONAL | Administration | M09 | Review moderation | No
M03 | M09 | CONDITIONAL | Administration | M09 | Listing moderation/configuration | No
M04 | M09 | CONDITIONAL | Administration | M09 | Learning configuration | No
M05 | M09 | CONDITIONAL | Administration | M09 | Event moderation | No
M06 | M09 | CONDITIONAL | Administration | M09 | Developer moderation | No
M07 | M09 | CONFIGURATION | Configuration | M09 | Administrative configuration path; M07 remains DBR authority | No
M12 | M09 | CONDITIONAL | Administration | M09 | Organization administration | No
M13 | M09 | CONFIGURATION | Configuration | M09 | Provider catalogue administration | No
M14 | M09 | CONDITIONAL | Administration | M09 | Commercial operations/reconciliation support | No
M15 | M09 | CONDITIONAL | Administration | M09 | Award administration | No
M11 | M09 | CONFIGURATION | Public discovery configuration | M09 | M09/applicable authoritative domain owns administrative lifecycle/configuration for Static Public Content and Announcement/Promotion surfaces observed by M11 | No
M03 | M12 | HARD / CONTEXT | Organization context | M12 | Organization listing context | Yes
M04 | M12 | CONDITIONAL | Organization context | M12 | Organization Learning/Session context | No
M14 | M12 | CONDITIONAL | Organization context | M12 | Organization commercial context | No
M15 | M12 | CONDITIONAL | Organization context | M12 | Organization qualification context | No
M03 | M02 | CONDITIONAL | Domain context | M02 | Agent profile/contact context | No
M03 | M06 | CONDITIONAL | Domain context | M06 | Approved Project may seed/create Listing; M03 owns Listing lifecycle | No
M05 | M06 | CONDITIONAL | Domain boundary | M06 | Project relationship to Event; M05 owns Event lifecycle/registration | No
M04 | M05 | CONDITIONAL | Domain boundary | M05 | Event ↔ Session relation; M05 owns Event, M04 owns Session | No
M03 | M14 | HARD — QUOTA/ENTITLEMENT | Commercial | M14 | Quota/entitlement/allowance consumed by Listing; M03 retains Listing/Refresh authority | Yes
M04 | M14 | CONDITIONAL | Commercial | M14 | Paid Learning/LP commercial fulfillment; M04 retains Learning truth | No
M15 | M04 | HARD — EVIDENCE | Qualification evidence | M04 | Learning/evidence production consumed by M15 | Yes
M15 | M14 | CONDITIONAL | Commercial evidence | M14 | Commercial evidence only where qualification rule explicitly permits; M15 decides qualification | No
M11 | M02 | OBSERVATIONAL | Discovery | M02 | Public profile representation | No
M11 | M03 | OBSERVATIONAL | Discovery | M03 | Public listing representation | No
M11 | M04 | OBSERVATIONAL | Discovery | M04 | Public learning/session representation | No
M11 | M05 | OBSERVATIONAL | Discovery | M05 | Public event representation | No
M11 | M06 | OBSERVATIONAL | Discovery | M06 | Public developer/project representation | No
M11 | M12 | OBSERVATIONAL | Discovery | M12 | Public organization representation | No
M11 | M15 | OBSERVATIONAL | Discovery | M15 | Public award/title representation | No
M08 | M02 | OBSERVATIONAL | Projection | M02 | Profile projection | No
M08 | M03 | OBSERVATIONAL | Projection | M03 | Listing/lead projection | No
M08 | M04 | OBSERVATIONAL | Projection | M04 | Learning/session projection | No
M08 | M05 | OBSERVATIONAL | Projection | M05 | Event notification | No
M08 | M06 | OBSERVATIONAL | Projection | M06 | Developer/project notification | No
M08 | M07 | OBSERVATIONAL | Projection | M07 | DBR dashboard/history | No
M08 | M12 | OBSERVATIONAL | Projection | M12 | Organization notification | No
M08 | M13 | OBSERVATIONAL | Projection | M13 | AI operational notification | No
M08 | M14 | OBSERVATIONAL | Projection | M14 | Commercial/payment notification | No
M08 | M15 | OBSERVATIONAL | Projection | M15 | Award notification | No

## Authority Register
module | scope | authority | reconciliation
M01 | Identity / User / Authentication | Identity authority | Preserve
M02 | Profile / Review | Profile/review authority | Preserve
M03 | Listing / Listing Lifecycle / Refresh | Listing + Refresh action/eligibility authority | Preserve + augment
M04 | Learning / Learning Economy / Session | Learning/session/evidence-production authority | Preserve + augment
M05 | Event / Registration | Event/registration authority | Preserve
M06 | Developer / Project / Marketing Kit / Claim | Developer/project/claim authority | Preserve + augment
M07 | DBR | DBR authority | Preserve
M08 | Dashboard / Notification Projection | Projection/notification authority | Preserve
M09 | Administration / Configuration / Audit | Administrative/configuration authority within underlying domain grants | Preserve + controlled augmentation
M10 | Authorization / RBAC / Permission / Scope / RLS | Authorization authority | Preserve + augment
M11 | SEO / Discovery / Analytics | Public discovery/SEO/measurement layer; not source-domain business authority | Preserve + augment
M12 | Organization / Membership / Context | Organization/membership/context authority | Preserve + current lifecycle
M13 | AI / BYOK / Provider Catalogue | AI/BYOK/provider domain authority | Preserve + controlled configuration
M14 | Commercial / Payment / Entitlement / Quota / Promotion | Commercial/payment/entitlement/quota/promotion authority | Preserve + current commercial decisions
M15 | Qualification / Evidence / Award | Qualification/Award authority; consumes governed upstream evidence | Preserve + augment

## Residual Register
id | finding | status | interpretation | disposition
P1-R01 | Physical schema/RLS implementation proof | CONTROLLED | Not a P1 semantic blocker | Downstream implementation/verification
P1-R02 | Runtime verification | CONTROLLED | Evidence-gated; absence does not invalidate semantic dependency contract | Downstream verification
P1-R03 | Exact endpoint identifiers where not evidenced | CONTROLLED | No invention; retain semantic/API-level dependency only | API/implementation stage
P1-R04 | Exact permission IDs / RLS SQL where not evidenced | CONTROLLED | M10 semantic authority remains valid without invented physical identifiers | Authorization/implementation stage
P1-R05 | Physical bootstrap ordering | PHYSICAL BOOTSTRAP | Implementation ordering only; not semantic authority | P2/P4
P1-R06 | Core package version-label mismatch | CONTROLLED | Outer package filename says v1.3 while internal root is v1.2; control/index artifacts carry v1.3 labels. Freeze authority is content/status hierarchy, not filename. | Retain as provenance/currentness note; do not silently relabel Core

## Cross Module
producer | consumer | relationship | authority_owner | contract
M09 | M11 | CONFIGURATION | M09 | Administrative lifecycle/configuration for Static Public Content and Announcement/Promotion where M09 is the applicable owner
M11 | M09 | OBSERVATIONAL/CONFIGURATION-CONSUMPTION | M09 | M11 exposes discovery/measurement; it does not own the administrative lifecycle
M14 | M03 | HARD — QUOTA/ENTITLEMENT | M14 | Commercial quota/allowance; M03 owns Listing/Refresh action
M03 | M14 | CONDITIONAL/CONTEXT | M03 | Listing/resource context returned to commercial domain without transferring Listing authority
M04 | M15 | HARD — EVIDENCE | M04 | Learning completion/evidence production
M15 | M04 | CONDITIONAL | M15 | Qualification interpretation may consume governed evidence
M14 | M15 | CONDITIONAL | M14 | Commercial evidence only where qualification rules permit
M05 | M04 | CONDITIONAL | M05/M04 | Event ↔ Session context; separate ownership
M12 | M03 | HARD / CONTEXT | M12/M03 | Organization context consumed by Listing
M12 | M14 | CONDITIONAL | M12/M14 | Organization context for commercial scope
M12 | M04 | CONDITIONAL | M12/M04 | Organization context for Learning/Session
M12 | M15 | CONDITIONAL | M12/M15 | Organization context for qualification
M06 | M03 | CONDITIONAL | M06/M03 | Approved Project may seed/create Listing; M03 owns lifecycle
M06 | M05 | CONDITIONAL | M06/M05 | Project relationship to Event; M05 owns lifecycle
M10 | M02–M15 | HARD — AUTHORIZATION | M10 | Authorization boundary; domain modules retain business authority
M01 | M02–M15 | HARD | M01 | Identity foundation
M11 | M02/M03/M04/M05/M06/M12/M15 | OBSERVATIONAL | Source domain | Public discovery/SEO/analytics; no business-state ownership
M08 | M02/M03/M04/M05/M06/M07/M12/M13/M14/M15 | OBSERVATIONAL | Source domain | Projection/notification only

## Gate
Gate | Result
Semantic blockers | 0
Dependency edges | 65
M11 public surfaces | 10
M09→M11 configuration edge | PRESENT
Physical/runtime proof blocking | NO
Final gate | PASS WITH CONTROLLED RESIDUALS